## Sheet1
MCS-QM-03A - INSPECTION & TEST PLAN TEMPLATE
Activity / Description | Reference Docs / Standards | Inspection Type (HP / WP / S / V) | Acceptance Criteria | Method / Test Procedure | Frequency | Responsible Party | Record / Form No. | Remarks / Notes
Excavation & Sub-grade Prep | ASTM D1557 / Project Specs | S / V | Compaction ≥ 95% MDD | Field Density Test | Each Lift | QC Inspector / 3rd Party Lab | QF-01 | Record moisture content
Formwork & Rebar Placement | ACI 318 / ASTM A615 | HP | Correct size & spacing, clean, secured | Visual Inspection & Checklist | Each Pour | QC Engineer | QF-02 | Submit photos before pour
Concrete Placement & Testing | ASTM C31 / C39 | HP / V | Slump ± 1", Temp ≤ 90°F, 28-day strength ≥ design | Slump, Temp, Cylinders | Each Load / Each Pour | QC & Lab Technician | QF-03 | Attach batch ticket & test report
Masonry Work Inspection | ASTM C90 / ACI 530 | S / V | Plumb ≤ 1/4", Mortar type as spec | Visual Inspection / Field Testing | Each Lift | QC Inspector | QF-04 | Daily photo log
Waterproofing Application | Manufacturer Spec / ASTM C836 | HP | Thickness & adhesion within tolerance | Adhesion Test / Visual | Each Area | QC / Manufacturer Rep | QF-05 | Include warranty cert
Structural Steel Fabrication & Welding | AWS D1.1 / AISC | HP | Weld size/profile per drawings, no cracks/porosity | VT / MT / UT | Per Lot / Per Joint Type | CWI / 3rd Party | QF-06 | Attach WPS / PQR
Painting & Coating | SSPC / NACE | WP | DFT per spec, adhesion OK | DFT Gauge / Visual | Each Coat | QC Inspector / Coating Rep | QF-07 | Record ambient conditions
Electrical Installations | NEC / NFPA 70 | S / V | Continuity & insulation test results OK | Multimeter / Insulation Tester | Per Circuit | E&I Inspector | E-01 | Tag cables before energizing
Final Inspection & Handover | Contract Docs | HP | All works complete & accepted | Walkdown / Punch List | Once | QC Manager / Client | QF-09 | Attach handover certificate