## Active Claims
MAGNUM CONSTRUCTION SERVICES INC.
LEGAL CLAIMS / DISPUTE RESOLUTION LOG
Document Code: MCS-CL-F07 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Claim ID | Project Name | Claim Type (Delay/Payment/Injury/Defect/Regulatory) | Date Notified | Parties Involved | Claim Value ($) | Status (Open/Under Review/Resolved/Closed) | Resolution Method (Negotiation/Mediation/Arbitration/Litigation) | Responsible Manager | Next Action Date | Next Action | Insurance Policy / Carrier | Notes / Evidence Ref
CLM-2025-001 | Harper Townhomes | Delay | 2025-10-05 | Owner / MCS | 150000 | Under Review | Mediation | Contracts Manager | 2025-11-10 | Mediation session | GL-225544 / Liberty | Chronology file QMS link
CLM-2025-002 | Edge at Dadeland | Payment | 2025-09-28 | MCS / Subcontractor | 82000 | Open | Negotiation | Project Manager | 2025-11-05 | Offer counter | — | Emails logged 10/20
CLM-2025-003 | Harper Townhomes | Injury | 2025-08-14 | Employee / MCS | 0 | Resolved | Negotiation | HSE Manager | 2025-09-01 | — | WC-88455 / Travelers | No lost time; release signed

## Financial Exposure
MAGNUM CONSTRUCTION SERVICES INC.
FINANCIAL EXPOSURE TRACKER
Document Code: MCS-CL-F07 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Claim ID | Project Name | Claim Value ($) | Legal Fees to Date ($) | Insurance Reserve ($) | Insurance Recovery ($) | Net Exposure ($) | Status | Last Updated | Notes
CLM-2025-001 | Harper Townhomes | #N/A | 12000 | 30000 | 0 | 0 | #N/A | 2025-10-25 | Awaiting mediation
CLM-2025-002 | Edge at Dadeland | Claim Value ($) | 3500 | 0 | 0 | #VALUE! | Status (Open/Under Review/Resolved/Closed) | 2025-10-25 | Negotiation
CLM-2025-003 | Harper Townhomes | 150000 | 0 | 5000 | 5000 | #N/A | Under Review | 2025-09-05 | Closed by release

## Dispute Calendar
MAGNUM CONSTRUCTION SERVICES INC.
DISPUTE CALENDAR
Document Code: MCS-CL-F07 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Claim ID | Event Type (Mediation/Hearing/Deposition/Deadline) | Event Date | Venue / Platform | Lead Counsel / Manager | Counterparty | Outcome / Notes | Next Step
CLM-2025-001 | Mediation | 2025-11-10 | JAMS Miami | Legal Counsel | Owner's Counsel | — | Prepare mediation brief
CLM-2025-002 | Negotiation Meeting | 2025-11-05 | Teams | Contracts Manager | Subcontractor PM | — | Counter proposal

## Dashboard
MAGNUM CONSTRUCTION SERVICES INC.
LEGAL CLAIMS DASHBOARD
Document Code: MCS-CL-F07 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Metric | Value | Status | Count
Total Claims | 4 | Open | 1
Open / Under Review | 2 | Under Review | 1
Resolved / Closed | 1 | Resolved | 1
Total Claimed Value ($) | 232000 | Closed | 0
Total Net Exposure ($) | #VALUE!
|  | Delay | 1
|  | Payment | 1
|  | Injury | 1
|  | Defect | 0
|  | Regulatory | 0