## TW Summary
MAGNUM CONSTRUCTION SERVICES INC.
TEMPORARY WORKS DESIGN & APPROVALS — SUMMARY
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Project Name: |  | Project Code:
Prime Contractor: | Magnum Construction Services Inc. | Discipline: | Concrete/Masonry/LGSF
Temporary Works Coordinator (TWC): |  | Temporary Works Supervisor (TWS):
Independent Checker: |  | Designer (Engineer of Record):
Design Basis Codes: | ACI/ASCE/OSHA/NDS | Client Spec Ref:
Review Cycle (days): | 7 | Register Owner: | Project Engineer

## Design Brief Register
MAGNUM CONSTRUCTION SERVICES INC.
TEMPORARY WORKS DESIGN BRIEF REGISTER
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Brief ID | Category | Location / Grid | Description | Design Constraints (Loads, Span, Soil) | Proposed Designer | Proposed Checker | Date Issued | Status | Remarks
BR-001 | Formwork | Grid B2-B6, L2 Slab | Slab formwork & shoring | LL 50 psf, span 18 ft | ABC Eng. | XYZ Eng. | 10/28/2025 | In Review | Need backpropping calc

## Temporary Works Register
MAGNUM CONSTRUCTION SERVICES INC.
TEMPORARY WORKS REGISTER (ITEM-BY-ITEM)
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
TW ID | Category | Design Ref / Drawing | Location | Owner (Sub/Prime) | TWS | Installation Start | Removal (Strike) Date | Inspection Freq (Daily/Wkly) | Status | Tag/Sign Posted (Y/N) | Remarks
TW-001 | Shoring | TW-SHR-2025-01 | Core Area L2 | Magnum | J. Rivera | 10/29/2025 |  | Daily | Open | Y | Backprop required after pour

## Calcs & Check Log
MAGNUM CONSTRUCTION SERVICES INC.
CALCULATIONS & INDEPENDENT CHECK LOG
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Calc Ref | TW ID / Brief ID | Designer | Checker | Design Code | Date Submitted | Date Checked | Check Category (Cat 1/2/3) | Outcome (Accept/Revise) | Remarks
CAL-001 | TW-001 / BR-001 | ABC Eng. | XYZ Eng. | ACI 347 / OSHA | 10/29/2025 | 10/30/2025 | Cat 2 | Accept | OK for issue IF issued

## Permits & Inspections
MAGNUM CONSTRUCTION SERVICES INC.
PERMITS & INSPECTIONS (SCAFFOLD/SHORING/EXCAVATION)
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Inspection/Permit Type | TW ID | Inspector/Agency | Required Frequency | Date | Result (Pass/Fail) | Defects / Actions | Closed (Y/N)
Scaffold Weekly | TW-002 | HSE / Competent Person | Weekly | 10/31/2025 | Pass | — | Y

## Load Test Log
MAGNUM CONSTRUCTION SERVICES INC.
LOAD TEST & COMMISSIONING LOG
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Test ID | TW ID | Type (Load/Proof/Leak) | Test Spec / Criteria | Date | Applied Load | Duration | Result (Pass/Fail) | Witnesses | Remarks
LT-001 | TW-001 | Load | 1.25 x design load | 10/31/2025 | 62 psf | 2 hr | Pass | QA/QC, Client Rep | No residual deflection

## Lifting Plans
MAGNUM CONSTRUCTION SERVICES INC.
LIFTING / HOISTING PLANS REGISTER
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Lift Plan ID | Equipment (Crane/Hoist) | Capacity | Lift Class (Std/Critical) | Load Description | Max Radius | Rigging Plan Ref | TWS Approval (Y/N) | Date Approved | Remarks
LP-001 | Tower Crane TC-01 | 20T | Std | Formwork tables | 35 m | RIG-2025-07 | Y | 10/30/2025 | —

## Erect & Strike Plan
MAGNUM CONSTRUCTION SERVICES INC.
ERECTION & STRIKE PLAN REVIEW
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Plan ID | TW ID | Install Method Statement Ref | Strike/Removal Method Ref | Backpropping Required (Y/N) | Cure Time / Strength Req | Hold Points / ITP Ref | Reviewer | Date Reviewed | Remarks
ESP-001 | TW-001 | MS-Form-Install-01 | MS-Form-Strike-01 | Y | 3000 psi @ 72 hr | ITP-Concrete-05 | QA/QC | 10/31/2025 | Strike after cylinders OK

## Variations & NCRs
MAGNUM CONSTRUCTION SERVICES INC.
VARIATIONS, WAIVERS & NCRs
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Ref No. | TW ID | Type (Variation/Waiver/NCR) | Description of Change/Issue | Raised By | Date Raised | Action Owner | Due Date | Status | Remarks
VAR-001 | TW-001 | Variation | Increase backpropping under grid C | TWS | 10/31/2025 | Designer | 11/02/2025 | Open | Await calc addendum

## Approvals & Certificates
MAGNUM CONSTRUCTION SERVICES INC.
APPROVALS & CERTIFICATES
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Approval ID | TW ID / Brief ID | Document Type (Drawing/Calc/Cert) | Rev | Approved By | Role (TWC/TWS/Client) | Date Approved | Distribution Issued (Y/N) | Remarks
APP-001 | TW-001 / BR-001 | Drawing | A | XYZ Eng. | Checker | 10/31/2025 | Y | Issued to site

## RAMS Log
MAGNUM CONSTRUCTION SERVICES INC.
RISK ASSESSMENT & METHOD STATEMENTS (RAMS) LOG
Document Code: MCS-OP-F14 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
RAMS ID | TW ID | Risk Assessment Ref | Method Statement Ref | Residual Risk Level (L/M/H) | HSE Review Date | TWS Review Date | Approved (Y/N) | Remarks
RAMS-001 | TW-001 | RA-Form-07 | MS-Formwork-03 | M | 10/30/2025 | 10/31/2025 | Y | —