## RFI Log
MAGNUM CONSTRUCTION SERVICES INC.
RFI, SUBMITTAL, AND TRANSMITTAL LOGS
Document Code: MCS-OP-F07 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
RFI No. | Date Issued | Subject / Description | Discipline | Issued To | Response Date | Status (Open / Closed) | Remarks
RFI-001 | 10/31/2025 | Clarification on beam detail at grid intersection | Structural | Consultant | 11/02/2025 | Closed | Issued revised drawing S-22

## Submittal Log
MAGNUM CONSTRUCTION SERVICES INC.
RFI, SUBMITTAL, AND TRANSMITTAL LOGS
Document Code: MCS-OP-F07 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Submittal No. | Date Submitted | Description / Material / Drawing | Vendor / Subcontractor | Discipline | Status (Approved / Revise & Resubmit) | Response Date | Remarks
SUB-010 | 10/30/2025 | Concrete Mix Design – 40 MPa | ABC Ready Mix | Civil | Approved | 11/01/2025 | Approved as Noted – use cement type I/II

## Transmittal Log
MAGNUM CONSTRUCTION SERVICES INC.
RFI, SUBMITTAL, AND TRANSMITTAL LOGS
Document Code: MCS-OP-F07A ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Transmittal No. | Date | Sent To | Subject / Content Description | Document References | Purpose (For Review / Info / Record) | Acknowledged By | Remarks
TRN-005 | 10/31/2025 | Consultant | Submission of revised architectural drawings A-101 to A-109 | A-101 to A-109 | For Review | R. Davis | Uploaded via Aconex Portal