## Monitoring Plan Summary
MAGNUM CONSTRUCTION SERVICES INC.
NOISE & VIBRATION MONITORING — PLAN SUMMARY
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Project Name: |  | Project Code:
Environmental Lead: |  | HSE Manager:
Monitoring Standard: | ANSI S1.4 / S1.11; FDOT; OSHA | Community Limit (dBA): | 65 day / 55 night (example)
Vibration Standard: | USBM RI 8507 / FTA | PPV Limit: | 0.5 in/s (example)
Monitoring Locations: | N1 North Boundary; N2 South Gate; V1 Core Area | Schedule: | Weekly + complaint-based

## Noise Monitoring Log
MAGNUM CONSTRUCTION SERVICES INC.
NOISE MONITORING LOG (dBA)
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date | Time | Location ID | Instrument ID | Noise Metric (Leq/Lmax...) | dBA | Wind (mph) | Weather | Limit Exceeded (Y/N) | Notes
2025-10-31 | 10:00 | N1 | SLM-01 | Leq | 62 | 8 | Clear | N | Baseline daytime reading
2025-11-01 | 21:00 | N2 | SLM-01 | Leq | 58 | 6 | Calm | N | Night shift, low traffic
2025-11-01 | 13:30 | N2 | SLM-01 | Lmax | 74 | 10 | Windy | Y | Impact hammer in use

## Vibration Monitoring Log
MAGNUM CONSTRUCTION SERVICES INC.
VIBRATION MONITORING LOG (PPV)
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date | Time | Location ID | Instrument ID | Unit (in/s or mm/s) | PPV | Dominant Freq (Hz) | Activity | Limit Exceeded (Y/N) | Notes
2025-10-31 | 10:15 | V1 | VM-01 | in/s | 0.22 | 18 | Compaction | N | Within comfort limit
2025-11-01 | 13:40 | V1 | VM-01 | in/s | 0.58 | 22 | Impact hammer | Y | Triggered corrective action

## Equipment & Calibration
MAGNUM CONSTRUCTION SERVICES INC.
EQUIPMENT & CALIBRATION REGISTER
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Instrument Type | ID | Make/Model | Serial No. | Calibration Date | Due Date | Certificate No. | In Service (Y/N) | Notes
Sound Level Meter | SLM-01 | NTi XL2 | SN-XL2-8891 | 2025-07-01 | 2026-07-01 | CAL-5591 | Y | Field calibrator 114 dB used
Vibration Monitor | VM-01 | Instantel Micromate | SN-MIC-2241 | 2025-06-15 | 2026-06-15 | CAL-5477 | Y | —

## Community Complaint Log
MAGNUM CONSTRUCTION SERVICES INC.
COMMUNITY COMPLAINT LOG
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Complaint ID | Date / Time | Complainant (Name/Addr) | Contact | Type (Noise/Vibration/Both) | Description | Initial Response | Investigation Result | Closed (Y/N)
C-001 | 2025-11-01 14:05 | Resident (123 Oak St.) | (555) 010-7788 | Noise | Loud hammering at midday | Reduced activity; applied barriers | Confirmed Lmax 74 dBA; rescheduled work | Y

## Exceedance & Corrective
MAGNUM CONSTRUCTION SERVICES INC.
EXCEEDANCE & CORRECTIVE ACTION LOG
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Ref ID | Date | Type (Noise/Vibration) | Location ID | Limit | Measured | Root Cause | Immediate Action | Follow-up Action | Closed (Y/N)
EX-001 | 2025-11-01 | Vibration | V1 | 0.5 in/s | 0.58 | Impact energy too high | Paused hammer; adjusted settings | Installed buffer pads; revised method | Y

## Dashboard
MAGNUM CONSTRUCTION SERVICES INC.
NOISE/VIBRATION DASHBOARD
Document Code: MCS-EN-F06 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Metric | Value
Avg Leq (dBA) | 60
Max Lmax (dBA) | 74
# Noise Exceedances | 1
Max PPV (in/s) | 0.58
# Vibration Exceedances | 1
Complaints Logged | 2
Noise | 1
Vibration | 0
Both | 0