## Incident & Spill Log
MAGNUM CONSTRUCTION SERVICES INC.
ENVIRONMENTAL INCIDENT & SPILL LOG
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | Date | Time | Project/Site | Type | Severity | Description (short) | Immediate Action | Injury (Y/N) | Reportable (Y/N) | Status | Owner | Open Days | Target Close | Actual Close | Days to Close
ENV-INC-001 | 2025-10-31 | 09:40 | Harper Townhomes | Spill- Fuel | Moderate | Diesel spill near GenPad (~5 gal) | Deployed spill kit, contained | N | N | Closed | HSE Manager | 45962 | 2025-11-01 | 2025-11-01 | 0
ENV-INC-002 | 2025-11-01 | 13:15 | Harper Townhomes | Air/Dust Exceedance | Minor | Visible dust at haul road | Applied water, reduced speeds | N | N | Open | Site Superintendent | #VALUE! | 2025-11-03

## Spill Report Details
MAGNUM CONSTRUCTION SERVICES INC.
SPILL REPORT — DETAILED INFORMATION
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | Spill Date | Material Spilled | Estimated Volume (gal/L) | Exact Location | GPS (if available) | Source (Tank/Hose/Equipment) | Cause | Contained On-Site (Y/N) | Reached Water/Drains (Y/N) | Weather | Soil/Surface Type | Photos (file refs) | Notes
ENV-INC-001 | 2025-10-31 | Diesel | 5 | GenPad South | 26.715,-80.058 | Hose quick-connect | Fitting failure | Y | N | Clear | Compacted gravel | photo_001.jpg; photo_002.jpg | Spill kit deployed within 5 min

## Investigation & Root Cause
MAGNUM CONSTRUCTION SERVICES INC.
INCIDENT INVESTIGATION & ROOT CAUSE ANALYSIS
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | Investigator | Investigation Date | Immediate Causes | Underlying Causes | Root Cause (5-Why) | Contributing Factors | Preventive Measures Proposed | Verified By | Verification Date
ENV-INC-001 | EHS Manager | 2025-11-01 | Hose failure | Maintenance frequency | Why1-5 analysis documented | Windy day; crowded laydown | Increase PM on hoses; guards | PM | 2025-11-02

## Corrective Action Tracker
MAGNUM CONSTRUCTION SERVICES INC.
CORRECTIVE ACTION TRACKER
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Action ID | Incident ID | Action Description | Owner | Due Date | Date Completed | Status | Effectiveness Verified (Y/N) | Remarks
CA-001 | ENV-INC-001 | Replace hose & install drip tray | Equipment Manager | 2025-11-02 | 2025-11-01 | Closed | Y

## Regulatory Notifications
MAGNUM CONSTRUCTION SERVICES INC.
REGULATORY NOTIFICATIONS REGISTER
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | Reportable (Y/N) | Agency | Contact / Case No. | Date/Time Reported | Reported By | Documents Sent | Follow-up Required (Y/N) | Due Date | Closed (Y/N)
ENV-INC-001 | N | [5 empty] | N |  | Y

## Waste Recovery & Disposal
MAGNUM CONSTRUCTION SERVICES INC.
WASTE RECOVERY & DISPOSAL TRACKING
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | Waste Type (Soil/Absorbents/Water) | Qty (tons/gal) | Container/Drum ID | Transporter | Facility | Manifest/Ticket No. | Date Shipped | Closed (Y/N)
ENV-INC-001 | Absorbents | 0.05 | DR-001 | GreenCycle Haul | County HHW Facility | WST-5590 | 2025-11-02 | Y

## Evidence Register
MAGNUM CONSTRUCTION SERVICES INC.
EVIDENCE REGISTER (PHOTOS/DOCS)
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Incident ID | File Ref | Type (Photo/Doc/Video) | Taken By | Date | Description / Notes
ENV-INC-001 | photo_001.jpg | Photo | A. Diaz | 2025-10-31 | Initial spill area
ENV-INC-001 | photo_002.jpg | Photo | A. Diaz | 2025-10-31 | Post-cleanup area

## Dashboard
MAGNUM CONSTRUCTION SERVICES INC.
ENVIRONMENTAL INCIDENT DASHBOARD
Document Code: MCS-EN-F10 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
KPI | Value | Type | Count
Total Incidents | 3 | Spill- Fuel | 1
Open Incidents | 1 | Spill- Oil | 0
Closed Incidents | 1 | Spill- Chemical | 0
Average Days to Close | 0 | Stormwater Discharge | 0
Reportable Events | 0 | Air/Dust Exceedance | 1
|  | Noise/Vibration Exceedance | 0
|  | Waste Non-Compliance | 0
|  | Wildlife/Vegetation | 0
|  | Other | 0
|  | Open | 1
|  | Closed | 1
|  | Pending | 0
|  | Monitoring | 0