## Insurance Certificates Register
MAGNUM CONSTRUCTION SERVICES INC.
INSURANCE CERTIFICATES REGISTER
Document Code: MCS-CL-F03 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Vendor / Subcontractor | Policy No. | Provider / Broker | Policy Type | Coverage Limit | Issue Date | Expiry Date | Status | Additional Insured (Y/N) | Notes
ABC Concrete LLC | GL-225544 | Liberty Mutual | General Liability | $2,000,000 | 2025-01-10 | 2026-01-10 | Valid | Y | —
SkyFrame Steel Inc. | WC-88455 | Travelers | Workers Compensation | Statutory | 2025-03-01 | 2025-12-31 | Expiring | Y | Renewal sent 10/15/25

## Bond Register
MAGNUM CONSTRUCTION SERVICES INC.
BOND REGISTER
Document Code: MCS-CL-F03 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Project Name | Bond Type (Bid/Perf/Pay/Maint) | Bond No. | Surety Company | Contract Value | Bond Value (%) | Effective Date | Expiry / Warranty End | Status | Notes
Harper Townhomes | Performance | PB-1022 | Allied Surety Co. | $2,500,000 | 100% | 2025-02-01 | 2026-02-01 | Valid | —
Edge at Dadeland | Payment | PB-1033 | Guardian Bond Group | $4,100,000 | 100% | 2025-05-01 | 2026-05-01 | Valid | —

## Renewal Alerts Log
MAGNUM CONSTRUCTION SERVICES INC.
RENEWAL ALERTS LOG
Document Code: MCS-CL-F03 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date Sent | Vendor | Policy / Bond No. | Responsible Party | Next Follow-up | Status | Comments
2025-10-10 | SkyFrame Steel Inc. | WC-88455 | Procurement Manager | 2025-10-25 | Pending | Awaiting renewal certificate

## Dashboard
MAGNUM CONSTRUCTION SERVICES INC.
INSURANCE & BOND DASHBOARD
Document Code: MCS-CL-F03 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Metric | Value
Total Policies | 3
Valid Policies | 1
Expiring Policies | 1
Expired Policies | 0
Total Bonds | 3