## Access Control Checklist
MAGNUM CONSTRUCTION SERVICES INC.
SITE SECURITY AND VISITOR MANAGEMENT PLAN
Document Code: MCS-OP-F11A ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Security Officer | Project | Gate Location | Perimeter Fence Condition | Lighting Operational | CCTV Working | Remarks
10/31/2025 | A. Smith | Palm Bay Apartments | Main Gate | OK | OK | OK | All systems operational

## Visitor Log
MAGNUM CONSTRUCTION SERVICES INC.
SITE SECURITY AND VISITOR MANAGEMENT PLAN
Document Code: MCS-OP-F11 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Visitor Name | Company | Purpose of Visit | Host / Escort | Time In | Time Out | Badge No. | Signature
J. Brown | Consultant | Progress Inspection | M. Gaya | 09:00 | 10:30 | V-011

## Vehicle Inspection Log
MAGNUM CONSTRUCTION SERVICES INC.
SITE SECURITY AND VISITOR MANAGEMENT PLAN
Document Code: MCS-OP-F11 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Vehicle No. | Driver Name | Company | Purpose of Entry | Inspection Status | Security Officer | Remarks
10/31/2025 | FL-3821 | C. Perez | Concrete Supply Co. | Material Delivery | Cleared | A. Smith | Delivery inspected - OK

## Security Patrol Record
MAGNUM CONSTRUCTION SERVICES INC.
SITE SECURITY AND VISITOR MANAGEMENT PLAN
Document Code: MCS-OP-F11 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Time | Security Officer | Patrol Area | Condition Observed | Action Taken | Next Patrol Scheduled | Remarks
10/31/2025 | 22:00 | J. Rivera | Material Storage Yard | No issues | — | 23:00 | All secure

## Incident Report Summary
MAGNUM CONSTRUCTION SERVICES INC.
SITE SECURITY AND VISITOR MANAGEMENT PLAN
Document Code: MCS-OP-F11 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Time | Reported By | Location | Incident Type | Description | Immediate Action Taken | Follow-Up / Status
10/31/2025 | 21:15 | A. Smith | Gate 2 | Suspicious Vehicle | Unauthorized truck approached gate | Security intervened, escorted off-site | Reported to PM - Resolved