## TCP Summary
MAGNUM CONSTRUCTION SERVICES INC.
TRAFFIC CONTROL & ROADWAY SAFETY PLAN — SUMMARY
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Project Name: | Project Code:
Roadway / Segment: | MOT Phase:
Prime Contact (PM): | Traffic Control Supervisor:
Jurisdiction (DOT/City/County): | MUTCD Ref: | Part 6
Work Hours (Std): | Night Work:
Police / Off-Duty Officers Required: | Emergency Contacts Posted (Y/N):

## Lane Closure Schedule
MAGNUM CONSTRUCTION SERVICES INC.
LANE CLOSURE SCHEDULE
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Phase | Date | Day | Roadway/Dir (NB/SB/E/W) | From Station / Cross St | To Station / Cross St | Closure Type (Full/Partial/Shoulder) | Start Time | End Time | TTCD Setup Complete (Y/N) | Remarks
Phase 1 | 11/05/2025 | Wed | NB | Main & 1st | Main & 3rd | Partial | 21:00 | 05:00 | N | Police detail booked

## Detours & Phasing
MAGNUM CONSTRUCTION SERVICES INC.
DETOURS & MOT PHASING
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Phase | Detour ID | Description / Route | TTCP Drawing Ref | Pedestrian Routing OK (Y/N) | Bus/School Route Impact (Y/N) | Sign Package Deployed (Y/N) | Remarks
Phase 1 | D-01 | EB traffic via Oak → Pine → 3rd Ave | TTCP-01 | Y | N | Y | Message board updated

## Device Inventory (MOT)
MAGNUM CONSTRUCTION SERVICES INC.
TEMPORARY TRAFFIC CONTROL DEVICE INVENTORY (MOT)
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Device Type (Cone/Barrel/Sign/Board) | Qty Required | Qty Deployed | Condition (OK/Damaged) | Last Inspection Date | Inspector | Replacement Needed (Y/N) | Remarks
Cone | 120 | 120 | OK | 10/31/2025 | TCS J. Alvarez | N | —
Sign | 12 | 12 | OK | 10/31/2025 | TCS J. Alvarez | N | R2-1, W20-1, W20-5 used

## Flagging Roster
MAGNUM CONSTRUCTION SERVICES INC.
FLAGGING ROSTER & CERTIFICATIONS
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Flagger Name | Employer | Certification Type (ATSSA/FDOT) | Cert No. | Expiry Date | Assigned Shift | Radio Channel | Notes
R. Lopez | Magnum | ATSSA | AT-55421 | 08/15/2026 | Night | Ch-1 | Paired with J. Singh

## Daily Work Zone Inspect
MAGNUM CONSTRUCTION SERVICES INC.
DAILY WORK ZONE INSPECTION CHECKLIST
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Shift | Inspector | Advance Warning Signs OK (Y/N) | Taper Length per MUTCD (Y/N) | Channelizing Devices OK (Y/N) | Ped Detour Safe (Y/N) | Posted Speed Adjusted (Y/N) | Lighting/Glare Acceptable (Y/N) | Notes / Corrective Actions
10/31/2025 | Night | TCS J. Alvarez | Y | Y | Y | Y | Y | Y | All compliant.

## Night Work Lighting Log
MAGNUM CONSTRUCTION SERVICES INC.
NIGHT WORK LIGHTING LOG
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Area / Station | Lighting Units In Service | Light Meter Reading (fc) | Glare to Traffic (Y/N) | Generator/Fuel OK (Y/N) | Supervisor | Notes
10/31/2025 | Main @ 2nd | 6 | 10 | N | Y | Night Supt M. Perez | —

## Incident & Near Miss Log
MAGNUM CONSTRUCTION SERVICES INC.
INCIDENT & NEAR MISS LOG
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Time | Location | Type (Incident/Near Miss) | Description | Involved Parties | Immediate Action | Reported To | Follow-Up Status (Open/Closed)
11/01/2025 | 22:40 | Main @ 3rd | Near Miss | Vehicle entered taper; no contact | Driver, TCS | Police notified, taper reset | PM / HSE | Open

## Permit & Coord Log
MAGNUM CONSTRUCTION SERVICES INC.
PERMIT & AGENCY COORDINATION LOG
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Permit No. | Jurisdiction | Type (Lane Closure/Detour/Night Work) | Date Applied | Date Issued | Expiry Date | Status (Open/Closed) | Notes
FDOT-25-117 | FDOT District 4 | Lane Closure | 10/20/2025 | 10/24/2025 | 12/15/2025 | Open | Includes police detail requirement

## Public Notification Log
MAGNUM CONSTRUCTION SERVICES INC.
PUBLIC NOTIFICATION LOG
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Notice ID | Audience (Residents/Business/Agency) | Method (Email/Flyer/Variable Sign) | Date Issued | Issued By | Summary / Route Impact | Response / Feedback | Follow-Up Required (Y/N)
N-001 | Residents | Flyer | 10/29/2025 | Comms / PM | Night closure Main St 9pm-5am | 2 calls logged | N

## Emergency Access Checklist
MAGNUM CONSTRUCTION SERVICES INC.
EMERGENCY ACCESS & RESPONSE CHECKLIST
Document Code: MCS-OP-F13 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Date | Area / Phase | Fire/EMS Access Maintained (Y/N) | Hospital Route Verified (Y/N) | Police Briefed (Y/N) | Tow Service on Call (Y/N) | Message Boards Updated (Y/N) | Notes
10/31/2025 | Phase 1 | Y | Y | Y | Y | Y | All first responders notified