## Hold Witness Schedule
MAGNUM CONSTRUCTION SERVICES INC.
HOLD POINT / WITNESS POINT SCHEDULE
Document Code: MCS-QM-F10A ¦ Revision: 1.0 ¦ Effective Date: 2025-11-01
Concrete pour placement | Structural | ITP-S-03 | During pour | WP | Slump / temperature / mix design | Client / MCS | 12 | Testing by third party
Activity / Process | Discipline | ITP Ref / Specification Clause | Inspection Stage | Type (HP / WP / SP) | Acceptance Criteria | Inspection Authority (Client / Consultant / MCS) | Notification Period (hr) | Remarks
Electrical cable termination | Electrical | ITP-E-04 / NEC | Before energizing | WP | Continuity & megger test results | Client / MCS | 12 | Tag and record megger values
HVAC duct pressure test | Mechanical | ITP-M-07 / SMACNA | Before commissioning | HP | Leakage ≤ 1 % of design flow | Consultant / MCS | 24 | Witness pressure gauge recording