## Safety Meeting Minutes
MAGNUM CONSTRUCTION SERVICES INC.
MEETING MINUTES (SAFETY, COORDINATION, PROGRESS)
Document Code: MCS-OP-F08A ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Meeting No. | Date | Location | Chairperson | Recorder | Meeting Type | Attendees | Key Discussion Points / Decisions
SM-001 | 10/31/2025 | Site Office | HSE Manager | Document Controller | Safety | All Site Supervisors | Reviewed PPE compliance; zero incidents reported; crane inspection scheduled for next week.

## Coordination Meeting Minutes
MAGNUM CONSTRUCTION SERVICES INC.
MEETING MINUTES (SAFETY, COORDINATION, PROGRESS)
Document Code: MCS-OP-F08 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Meeting No. | Date | Location | Chairperson | Recorder | Meeting Type | Attendees | Key Discussion Points / Decisions
CM-001 | 11/01/2025 | Conference Room | Project Manager | Document Controller | Coordination | All Subcontractors | Discussed sequencing of slab pour and delivery schedule for rebar; updated logistics plan approved.

## Progress Meeting Minutes
MAGNUM CONSTRUCTION SERVICES INC.
MEETING MINUTES (SAFETY, COORDINATION, PROGRESS)
Document Code: MCS-OP-F08 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Meeting No. | Date | Location | Chairperson | Recorder | Meeting Type | Attendees | Key Discussion Points / Decisions
PM-001 | 11/02/2025 | Client Office | Project Manager | Document Controller | Progress | Client, Consultant, Project Team | Reviewed overall 62% completion; delay on façade work due to material shipment; recovery plan initiated.

## Action Item Register
MAGNUM CONSTRUCTION SERVICES INC.
MEETING MINUTES (SAFETY, COORDINATION, PROGRESS)
Document Code: MCS-OP-F08 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Item No. | Meeting Ref | Description of Action / Issue | Responsible Person | Target Date | Status (Open / Closed) | Remarks
1 | SM-001 | Submit revised crane lifting plan | HSE Manager | 11/05/2025 | Open | Awaiting new crane vendor confirmation
2 | CM-001 | Coordinate rebar delivery and placement schedule | Site Engineer | 11/06/2025 | Closed | Completed 11/05/2025
3 | PM-001 | Finalize façade material import documentation | Procurement Manager | 11/10/2025 | Open | Pending customs release