## DCR Summary
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09A¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Project Name: |  | Project Code:
Date: |  | Day:
Weather (☀️/🌧): |  | Temperature (°C):
Prepared By: |  | Reviewed By:
Shift: |  | Location:
Work Completed Today | Work Planned for Tomorrow | Delays / Issues | Coordination Notes
Slab pour Grid C completed | Rebar Level 3 installation | Façade panel delay | Revised crane schedule approved

## Manpower Log
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Trade / Discipline | Subcontractor / Crew | No. of Workers | Hours Worked | Supervisor / Foreman | Remarks
Masonry | ABC Masonry LLC | 12 | 96 | R. Lopez | Blockwork Level 2
Electrical | VoltPro MEP | 8 | 64 | J. Singh | Rough-in works Level 1

## Equipment Log
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Equipment ID | Type / Description | Operator | Hours Used | Condition (OK/Defective) | Remarks
EXC-002 | Excavator CAT 320 | M. Perez | 8 | OK | Excavation for footing F2

## Material Deliveries
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Delivery No. | Supplier / Vendor | Material Description | Quantity / Unit | Received By | Inspection Status | Remarks
101 | Concrete Supply Co. | Ready Mix Concrete 40 MPa | 60 m³ | QA/QC | Accepted | Slab pour approved

## Inspections & Tests
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Inspection / Test | Location / Reference | Conducted By | Result | Remarks
Slump Test | Slab Grid C | QA/QC | Passed | 100mm slump recorded

## Safety Observations
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Observation | Action Required | Responsible Person | Target Date | Status (Open/Closed) | Remarks
Workers without safety vests | Provide replacements immediately | HSE Officer | 11/01/2025 | Closed | PPE reissued

## Visitors Log
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Name | Company / Role | Purpose of Visit | Time In | Time Out | Remarks
J. Brown | Consultant | Progress inspection | 9:00 AM | 10:30 AM | Structural approvals

## Summary & Sign-Off
MAGNUM CONSTRUCTION SERVICES INC.
DAILY CONSTRUCTION REPORT (DCR)
Document Code: MCS-OP-F09 ¦ Revision: 1.0 ¦ Effective Date: October 31 2025
Prepared By | Reviewed By | Approved By | Date | Remarks
Site Engineer | Project Manager | QA/QC Manager | 10/31/2025 | Report verified and filed