## SWPPP Inspection Checklist
MAGNUM CONSTRUCTION SERVICES INC.
SWPPP INSPECTION CHECKLIST
Document Code: MCS-EN-F04 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date | Inspector | BMP ID / Location | BMP Type (Silt Fence, Inlet, Basin, Washout, etc.) | Condition (Pass/Fail/Pend) | Corrective Action Needed (Y/N) | Comments | Photo Ref
2025-10-31 | EHS Tech A. Diaz | BMP-01 | Silt Fence | Pass | N | No sediment breach | photo_001.jpg

## Rainfall & Storm Log
MAGNUM CONSTRUCTION SERVICES INC.
RAINFALL & STORM EVENT LOG
Document Code: MCS-EN-F04 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date | Time | Rainfall (in) | Cumulative Storm (in) | Storm Event (Y/N) | Post-Rain Inspection Completed (Y/N) | Inspector | Notes
2025-10-31 | 08:00 | 0.35 | 0.35 | Y | Y | HSE Manager | Post-storm inspection triggered

## Corrective Action Log
MAGNUM CONSTRUCTION SERVICES INC.
SWPPP CORRECTIVE ACTION REGISTER
Document Code: MCS-EN-F04 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Action ID | Date Identified | BMP/Area | Issue Description | Responsible Party | Target Completion | Actual Completion | Status (Open/Closed/Pending) | Verification (Y/N) | Remarks
CA-001 | 2025-10-31 | BMP-05 | Sediment fence torn | Site Foreman | 2025-11-02 | 2025-11-01 | Closed | Y | Repaired & photo verified

## Dewatering Monitoring Log
MAGNUM CONSTRUCTION SERVICES INC.
DEWATERING MONITORING LOG
Document Code: MCS-EN-F04 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Date | Location / Discharge Point | Operation Type | Flow Rate (gpm) | Duration (hrs) | Visual Clarity (Clear/Muddy/Sheen) | Turbidity (NTU) | Sample Taken (Y/N) | Results / Comments | Inspector
2025-10-30 | Outfall 1 - North Basin | Dewatering | 150 | 2 | Clear | 45 | Y | NTU within limits | Env. Tech L. Rivera

## Permit & Outfall Register
MAGNUM CONSTRUCTION SERVICES INC.
PERMIT & OUTFALL REGISTER
Document Code: MCS-EN-F04 ¦ Revision: 1.0 ¦ Effective Date: November 1 2025
Permit Type | Permit No. | Issue Date | Expiry Date | Outfall ID / Location | Receiving Waterbody | Permittee / Owner | Notice of Termination (Y/N) | Comments
NPDES CGP | FLR123456 | 2025-09-01 | 2026-09-01 | Outfall 1 | Indian River Lagoon | Magnum Construction Services | N | Active permit for grading works